PROJECT PLAN: END-TO-END MACHINE LEARNING PIPELINE
Telecom Customer Churn Prediction System Using Python

Week 1 Task: Project Planning and Strategy
Date: August 19, 2026
Duration: 30-35 Hours Planning Phase

# Table of Contents

1. Introduction

2. Literature Review & Research Insights

3.Problem Definition

- 3.1 Problem Statement

- 3.2 Input Data

- 3.3 Potential Challenges

- 3.4 Expected Outcomes

4. Project Objectives

5. Methodology & Strategic Roadmap

6. Detailed Project Timeline (Phased Approach)

7. Milestones and Deliverables

8. Resource Requirements

- 8.1 Software & libraries

- 8.2 Computational Resources

- 8.3 Human Resources

- 8.4 Data Resources

9. Risk Management & Mitigation Plan

10. Data Strategy & Governance

11. Deployment Planning & MLOps Strategy

12. Evaluation Metrics & Success Criteria

13. Conclusion

14. References

# 1. Introduction

This project plan outlines the strategy for designing and implementing a complete end-to-end Machine Learning (ML) pipeline in Python for Telecom Customer Churn Prediction. In the highly competitive telecom industry, customer retention is significantly more cost-effective than acquisition. Churn rates of 15-25% annually pose a major revenue risk.

An ML pipeline automates the entire workflow from raw data ingestion to model deployment and monitoring, ensuring reproducibility, scalability, and maintainability. This document serves as a blueprint for the next 8-10 weeks of implementation (Weeks 2-10) and demonstrates strategic planning, forecasting, and risk-aware design expected in production ML projects.

The chosen problem domain is Customer Churn Prediction, which is a supervised binary classification problem with high business value, availability of public datasets (Kaggle IBM Telco Churn), and clear deployment potential as a REST API and dashboard.

# 2. Literature Review & Research Insights

Brief review of publicly available information:

IBM Telco Dataset (7043 rows, 21 features): Most cited dataset for churn. Studies show XGBoost and Random Forest achieve 80-84% accuracy, while deep learning offers marginal gains.

CRISP-DM Framework: Industry standard for ML lifecycle – Business Understanding, Data Understanding, Preparation, Modeling, Evaluation, Deployment.

MLOps Practices (Google, AWS whitepapers): Emphasis on CI/CD for ML, feature stores, model registry, data drift detection. Tools like MLflow, DVC, and Docker are critical.

Research Gap: Many academic projects stop at model training. This project focuses on end-to-end automation, explainability (SHAP), and deployment planning – addressing production readiness.

Python Ecosystem Trends: Scikit-learn for baseline, XGBoost/LightGBM for tabular SOTA, Imbalanced-learn for SMOTE, SHAP for explainability, FastAPI for deployment.

Key Insight: Churn prediction is not just a classification task but a business decision system requiring threshold tuning for precision vs recall tradeoff and cost-sensitive learning.

# 3. Problem Definition

3.1 Problem Statement: To develop an automated ML pipeline that predicts whether a telecom customer will churn (leave the service) in the next month based on demographics, service usage, contract details, and billing information, enabling proactive retention strategies.

3.2 Input Data:

Demographics: Gender, SeniorCitizen, Partner, Dependents

Account Information: Tenure (months), Contract (Month-to-month, One year, Two year), PaperlessBilling, PaymentMethod

Services: PhoneService, MultipleLines, InternetService (DSL, Fiber), OnlineSecurity, TechSupport, StreamingTV etc.

Billing: MonthlyCharges, TotalCharges

Target: Churn (Yes/No) – Binary label, expected class imbalance ~26.5% churn vs 73.5% retained

3.3 Potential Challenges:

Class Imbalance: Churn class is minority – requires SMOTE, class weights, or stratified sampling.

Data Quality: Missing values in TotalCharges, outliers in MonthlyCharges, inconsistent categorical encoding.

Feature Leakage: TotalCharges highly correlated with Tenure – careful handling needed.

Model Interpretability: Business stakeholders need reasons for churn, not just predictions – requires SHAP/LIME.

Concept Drift: Customer behavior changes over time; model performance degrades without monitoring.

3.4 Expected Outcomes: A production-ready pipeline with >82% accuracy, >0.84 ROC-AUC, recall >75% for churn class, SHAP dashboard for explainability, and a deployable FastAPI endpoint with <200ms latency.

# 4. Project Objectives

Primary Objective: Build an automated, reproducible ML pipeline covering ingestion → preprocessing → feature engineering → training → evaluation → deployment.

Technical Objectives: (a) Implement data validation using Great Expectations/Pydantic, (b) Compare at least 5 algorithms (Logistic Regression, Random Forest, XGBoost, LightGBM, CatBoost), (c) Hyperparameter tuning via Optuna, (d) Achieve ROC-AUC >=0.84

Business Objectives: Reduce churn by 10% through early intervention, identify top 3 churn drivers, provide actionable customer segmentation.

MLOps Objectives: Version control data/models with DVC & MLflow, containerize with Docker, implement CI/CD with GitHub Actions, enable monitoring for data drift.

Documentation Objective: Maintain clear, numbered documentation with experiment tracking and model cards.

# 5. Methodology & Strategic Roadmap

We follow CRISP-DM + MLOps hybrid roadmap with 6 phases:

| Phase | Key Tasks | Tools/Libraries | Output |
| --- | --- | --- | --- |
| 1. Business & Data Understanding | Problem framing, EDA, Data profiling | Pandas, Matplotlib, Seaborn, ydata-profiling | EDA Report, Data Dictionary |
| 2. Data Preparation | Cleaning, Encoding, Scaling, SMOTE, Feature Eng. | Scikit-learn, imblearn, Feature-engine | Cleaned dataset, preprocessing pipeline.pkl |
| 3. Modeling | Baseline + Advanced models, Cross-validation | XGBoost, LightGBM, Optuna, MLflow | Trained models, leaderboard |
| 4. Evaluation & Explainability | Metrics, SHAP, Error analysis | SHAP, LIME, sklearn.metrics | Evaluation report, SHAP plots |
| 5. Deployment Planning | API, Docker, CI/CD, Monitoring design | FastAPI, Docker, MLflow Registry | API spec, Dockerfile |
| 6. Documentation & Handover | Final report, DOC file, PPT | Sphinx, python-docx | Final DOC with TOC |

Critical Path: Data Preparation -> Modeling -> Evaluation is the longest dependency chain. Modeling cannot start without clean pipeline. Deployment planning runs parallel to evaluation after baseline model is ready.

Strategic Approach: Start with simple baseline (Logistic Regression) in Week 2 to validate pipeline, then iterate to complex models. Use modular code structure: src/data/, src/features/, src/models/, src/api/.

# 6. Detailed Project Timeline (Phased Approach)

Total Estimated Effort: 30-35 hours for planning, 80-100 hours for implementation (Weeks 2-10). Below is the detailed timeline for full project:

| Week | Phase | Tasks (30-35h breakdown for Week 1) | Deadline | Dependencies |
| --- | --- | --- | --- | --- |
| Week 1 | Project Planning (Current) | Literature review (6h), Problem definition (5h), Timeline & Milestones (6h), Risk/Resource analysis (5h), Documentation (8h) | Day 7 | None |
| Week 2 | Data Acquisition & EDA | Dataset download, EDA, profiling, imbalance check, hypothesis testing | Day 14 | Week 1 plan |
| Week 3 | Data Preprocessing Pipeline | Build sklearn Pipeline, handle missing, encoding, scaling, SMOTE, save pipeline | Day 21 | Week 2 EDA |
| Week 4 | Feature Engineering & Selection | Create Tenure Groups, Charge ratios, RFE, correlation analysis | Day 28 | Week 3 pipeline |
| Week 5 | Baseline Modeling | LogReg, Decision Tree, Random Forest with 5-fold CV, MLflow logging | Day 35 | Week 4 features |
| Week 6 | Advanced Modeling & Tuning | XGBoost, LightGBM, CatBoost, Optuna tuning (50 trials) | Day 42 | Week 5 baseline |
| Week 7 | Evaluation & Explainability | ROC-AUC, PR curve, confusion matrix, SHAP summary, model card | Day 49 | Week 6 models |
| Week 8 | Deployment Prep | FastAPI app, input validation, Dockerize, MLflow Model Registry | Day 56 | Week 7 final model |
| Week 9 | Testing & Monitoring | Unit tests, API load test, drift detection design, CI/CD | Day 63 | Week 8 API |
| Week 10 | Final Documentation | Final DOC, README, presentation, demo video | Day 70 | All phases |

Gantt Critical Path: W2->W3->W4->W5->W6->W7->W8. Any delay in data preparation directly impacts modeling milestones. Mitigation: Keep preprocessing modular and test with subset data.

# 7. Milestones and Deliverables

| Milestone ID | Milestone | Deliverable | Success Criteria | Review Date |
| --- | --- | --- | --- | --- |
| M1 | Project Plan Approved | This DOC file with TOC | Clarity >=9/10, completeness | Week 1 Day 7 |
| M2 | EDA Complete | EDA notebook + report (PDF) | All features profiled, insights documented | Week 2 Day 14 |
| M3 | Preprocessing Pipeline Ready | preprocess.py + pipeline.pkl | Handles unseen categories, >95% test coverage | Week 3 Day 21 |
| M4 | Baseline Model >75% Accuracy | MLflow runs + baseline metrics | ROC-AUC >0.75 | Week 5 Day 35 |
| M5 | Optimized Model >84% ROC-AUC | Best model + hyperparams + SHAP | Recall churn >75%, ROC-AUC >=0.84 | Week 7 Day 49 |
| M6 | API Deployed Locally | FastAPI /predict endpoint + Docker | Latency <200ms, 100% test pass | Week 8 Day 56 |
| M7 | Project Handover | Final DOC, GitHub repo, Demo | All evaluation criteria met | Week 10 Day 70 |

# 8. Resource Requirements

8.1 Software & Libraries:

Core Python: Python 3.10+, pandas 2.0, numpy 1.24, scikit-learn 1.3

Modeling: XGBoost 2.0, LightGBM 4.0, CatBoost, imbalanced-learn 0.11

Optimization & Tracking: Optuna 3.4, MLflow 2.7, DVC 3.0

Explainability: SHAP 0.44, LIME

Deployment: FastAPI 0.104, Uvicorn, Docker 24, Pydantic 2.5

Quality: pytest, great-expectations, Black, Flake8

Environment: Jupyter Lab, VS Code, Git & GitHub

8.2 Computational Resources: Laptop with 8GB RAM minimum, 16GB recommended; No GPU required for tabular data; Storage ~2GB for datasets/models; Cloud optional: AWS EC2 t2.medium or Google Colab for training.

8.3 Human Resources: 1 ML Engineer (you), 1 Mentor/Reviewer for weekly evaluation, Stakeholder (Business Analyst) for requirement validation.

8.4 Data Resources: IBM Telco Churn dataset (Kaggle), Synthetic data for API testing, External benchmarks: Papers from IEEE Xplore on churn prediction.

# 9. Risk Management & Mitigation Plan

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Data leakage & poor quality | Medium | High | Implement validation checks with Pydantic, use train/test split BEFORE any imputation, log data profile |
| R2 | Class imbalance leads to biased model | High | High | Use SMOTE + class_weight='balanced', evaluate on PR-AUC & F1 not just accuracy, stratified KFold |
| R3 | Overfitting on tuned models | Medium | Medium | Use nested CV, early stopping in XGB, regularization, keep holdout test set untouched |
| R4 | Scope creep – adding too many features/models | Medium | Medium | Strict MoSCoW prioritization, MVP first (baseline), timebox each phase |
| R5 | Deployment failure / environment mismatch | Low | High | Dockerize early, requirements.txt freeze, test API with pytest |
| R6 | Concept drift after deployment | High | Medium | Design monitoring with Evidently AI, retraining schedule monthly, log predictions |
| R7 | Timeline slippage (30-35h exceeded) | Medium | Low | Daily 2h focused blocks, use Pomodoro, maintain Kanban board in Notion/Trello |

Contingency Plan: If ROC-AUC <0.80 after tuning, fallback to ensemble stacking and additional feature engineering (interaction features). If time short, skip CatBoost and prioritize XGBoost + SHAP.

# 10. Data Strategy & Governance

Data Versioning: Use DVC to version data/ folder; raw data immutable, processed data versioned.

Privacy & Ethics: No PII beyond telecom usage; anonymize customer IDs; ensure GDPR compliance – no personal identifiers used for modeling; Fairness check: Evaluate model performance across gender and senior citizen groups.

Data Validation: Schema checks – Tenure 0-72, MonthlyCharges >0; TotalCharges numeric; Contract values constrained. Use Great Expectations.

Storage: /data/raw/, /data/processed/, /models/, /reports/ – standard Cookiecutter Data Science structure.

# 11. Deployment Planning & MLOps Strategy

Architecture: Client -> FastAPI (POST /predict with JSON) -> Preprocessing Pipeline (pkl) -> Model (pkl from MLflow Registry) -> Prediction + SHAP explanation -> Response JSON {churn_probability, churn_label, top_reasons}.

MLOps Workflow: (1) Git push triggers GitHub Actions: run pytest + flake8, (2) MLflow logs params/metrics/artifacts, (3) Best model promoted to Production stage in Registry, (4) Docker image built and pushed to Docker Hub, (5) Monitoring: Log prediction distribution, alert if churn rate prediction deviates >15% from baseline.

Scalability: Stateless API, horizontal scaling via Docker Compose; future: Kubernetes, Feature Store (Feast).

Rollback Plan: Keep last 2 model versions in registry; if production accuracy drops >5%, auto-rollback to previous version.

# 12. Evaluation Metrics & Success Criteria

Primary Metrics: ROC-AUC (>=0.84 target), PR-AUC (for imbalanced), Recall for Churn class (>=0.75 – we prefer catching churners even at cost of precision)

Secondary Metrics: Accuracy (>=0.82), F1-Score (>=0.72), Precision (>=0.65)

Business Metrics: Expected cost saving = (True Positive * retention offer cost) – False Positive cost; Lift chart top decile >3x

Explainability Metric: SHAP top 5 features should align with business intuition (Contract, Tenure, Fiber + TechSupport, MonthlyCharges)

Engineering Metrics: Pipeline reproducibility (same seed = same result), API latency <200ms, Code coverage >80%

# 13. Conclusion

This project plan establishes a clear, feasible, and business-aligned roadmap for building a complete ML pipeline for churn prediction. By following phased development, rigorous risk management, and MLOps best practices, the project ensures not only high model accuracy but also production readiness, interpretability, and maintainability. Week 1 planning (30-35 hours) is critical to avoid rework in later phases and provides the strategic foundation for Weeks 2-10. The next immediate step is to initiate Week 2 EDA following the structure outlined in Section 6.

# 14. References

IBM Telco Customer Churn Dataset – Kaggle (https://www.kaggle.com/datasets/blastchar/telco-customer-churn)

CRISP-DM Methodology – IBM Documentation

MLflow Documentation – https://mlflow.org/docs/latest/index.html

SHAP Documentation – Lundberg et al., 2017

Google MLOps Whitepaper – 'Practitioners Guide to MLOps'

Scikit-learn, XGBoost, LightGBM official docs